# DAXDA.IA 90-Day Execution Plan

Repository packet for JumpStart initial intake and regional startup support conversation

Operating logic The next 90 days should convert an impressive framework into evidence: interviews, pilots, reviewer feedback, workflow artifacts, and capital-ready proof.

# 90-day milestone map

| Window | Theme | Work | Evidence produced |
| --- | --- | --- | --- |
| Days 1-15 | Company readiness | Finalize naming, one-pager, deck, founder roles, legal formation plan, IP log, and customer-discovery script. | Clean packet; founder narrative; target list; meeting tracker. |
| Days 16-30 | Customer discovery | Run 15-25 interviews with legal, compliance, enterprise software, research, and civic teams. | Interview notes; pattern map; top 3 pain points; pilot criteria. |
| Days 31-45 | Pilot workflow | Define a narrow deidentified review workflow and scoring rubric. | Pilot protocol; audit template; risk scoring rubric; demo examples. |
| Days 46-60 | External validation | Recruit 2-4 outside reviewers/advisors to review process quality and market fit. | Reviewer memo; objections log; revisions list. |
| Days 61-75 | Design-partner pilots | Run 1-3 controlled pilot reviews using deidentified sample outputs. | Before/after audit artifacts; usability feedback; improvement claims limited to observed evidence. |
| Days 76-90 | Capital readiness | Convert evidence into a fundable narrative and program application package. | Updated deck; customer evidence; pilot results; ask; budget; roadmap. |

# Weekly cadence

Monday: planning, outreach queue, and JumpStart/advisor follow-ups.

Tuesday-Wednesday: customer discovery calls and notes.

Thursday: product workflow and audit template refinement.

Friday: evidence review, founder meeting, next-week plan, and follow-up emails.

Weekend: documentation cleanup only; no strategic panic builds.

# Key performance indicators

20-40 target accounts identified.

15-25 customer discovery conversations completed.

2-4 reviewers/advisors engaged.

1-3 deidentified design-partner pilots scoped or completed.

One repeatable audit template and scoring rubric.

One revised deck with evidence, not just theory.

# Risks to control

Overclaiming maturity before proof exists.

Explaining recursion mechanics before the buyer understands the business problem.

Pursuing too many verticals at once.

Skipping customer discovery and trying to sell too early.

Using private receipts in external conversations before they are organized and relevant.